## Sheet1
Threats | [6 empty] | Opportunities | [6 empty] | Risk | Probability | Impact | Risk Score | Ranking
Probability | Very High - 5 | 5 | 10 | 15 | 20 | 25 | 25 | 20 | 15 | 10 | 5 | Very High - 5 | Probability | Integrator needing paid and the PO is taking longer to approve internally | 4 | 5 | 20 | 1
[14 empty] | Needing additional money for unforseen modifications to the existing line | 3 | 5 | 15 | 2
[14 empty] | Integrator needing additional time for development | 3 | 4 | 12 | 3
| High - 4 | 4 | 8 | 12 | 16 | 20 | 20 | 16 | 12 | 8 | 4 | High - 4 |  | Install takes longer than anticipated | 3 | 4 | 12 | 4
[14 empty] | Shortage of maintenance workers to assist during install | 2 | 5 | 10 | 5
[14 empty] | Shortage of contractors available to assist during install | 2 | 5 | 10 | 6
| Medium - 3 | 3 | 6 | 9 | 12 | 15 | 15 | 12 | 9 | 6 | 3 | Medium - 3 |  | Initial hardware taking longer to acquire due to supply chain issues | 2 | 5 | 10 | 7
[14 empty] | Needing additional money for additional items | 3 | 3 | 9 | 8
[14 empty] | Critical hardware failure renders hardware unuseable | 1 | 5 | 5 | 9
| Low - 2 | 2 | 4 | 6 | 8 | 10 | 10 | 8 | 6 | 4 | 2 | Low - 2 |  | Natural disaster happens at integrators development site | 1 | 5 | 5 | 10
[14 empty] | Install gets pushed back to due install engineers availability | 1 | 4 | 4 | 11
[14 empty] | Cell fails to meet safety standards | 2 | 2 | 4 | 12
| Very Low - 1 | 1 | 2 | 3 | 4 | 5 | 5 | 4 | 3 | 2 | 1 | Very Low - 1 |  | Items held in the shipping port for additional time | 1 | 3 | 3 | 13
[14 empty] | Integrator fails acceptance testing | 1 | 2 | 2 | 14
|  | Very Low - 1 | Low - 2 | Medium - 3 | High - 4 | Very High - 5 | Very High - 5 | High - 4 | Medium - 3 | Low - 2 | Very Low - 1
|  | Negative Impact |  |  |  |  | Positive Impact